## Main Cutover Plan
Step ID | Step Last edited by | Category | Must wait for step # | Must wait until step # done | Step Readiness Status | AREA- FIN | AREA- MFG | AREA-WH | AREA-HR | AREA-IT | System | Step description | Step link to further data | Result validated by | Central / Local | Primary Assigned to | Secondary Assigned to | Area Lead | Go-Live PLAN |  |  |  | Go-Live ACTUAL |  |  |  | Schedule Impact |  | Rehearsal PLAN #n |  |  | Rehearsal ACTUAL #n |  |  |  | Schedule Impact |  | Rollback impact | To Do | Notes
[19 empty] | Start | Duration [hh:mm) | End | Status | Start | End | Duration [hh:mm) | Status | Duration Ahead/Behind | Cumulative impact (+/--) | Start | End | Status | Start | End | Duration [hh:mm) | Status | Duration Ahead/Behind | Cumulative Impact (+/-)
Firebreak/Review Call#1
Steps Continued..
Note on A1: Ajit Kotwal: Unique ID for each step. Consider IDs categorised per major section
Note on B1: Ajit Kotwal: Who last edited this step - this gies traceability across versions and who to contact for any questions
Note on C1: Ajit Kotwal: Categorise by type of step: e.g. Data Migration, Validation, Setup etc..
Note on D1: Ajit Kotwal: Dependent on which Step ID
Note on E1: Ajit Kotwal: Which Step ID must not start until this step is complete
Note on F1: Ajit Kotwal: Is the step definition is clear and ready to be executed. Green = Ready Amber =Potential risk Red = Blocked
Note on G1: Ajit Kotwal: Tick if step impacts this area
Note on L1: Ajit Kotwal: Which system does this step impact?
Note on M1: Ajit Kotwal: Description of the step
Note on N1: Ajit Kotwal: Link to any further document/material that describes the step and its validation
Note on O1: Ajit Kotwal: Who validated that the step was performed and matched the expected results
Note on P1: Ajit Kotwal: To be managed by central team or by the local team
Note on Q1: Ajit Kotwal: Who is the primary person assigned to perform this step
Note on R1: Ajit Kotwal: Who is the backup person assigned to perform this step
Note on S1: Ajit Kotwal: Person who is the lead for this area - for escalations and decisions
Note on AM1: Ajit Kotwal: If this step has any specific impact on rollback should be considered here
Note on AN1: Ajit Kotwal: Any remaining work needed for this step definition to be ready for use in the cutover defined here
Note on AO1: Ajit Kotwal: Any notes for this step?
Note on T2: Ajit Kotwal: Planned start time
Note on U2: Ajit Kotwal: Planned duration for this step
Note on W2: Ajit Kotwal: Status of the step: Skipped Failed Done
Note on X2: Ajit Kotwal: Actual Start Time
Note on Y2: Ajit Kotwal: Actual End Time
Note on Z2: Ajit Kotwal: Actual duration of step
Note on AA2: Ajit Kotwal: Status of the step: Skipped Failed Done
Note on AB2: Ajit Kotwal: The difference in amount (mins) taken compared to the planned duration (Plus for execess, minus for delay)
Note on AC2: Ajit Kotwal: The cumulative total of all the time saved and delays compared to the planned duration

## Contacts and calendar
Area Lead | Area | Contact name | Email | Working hours Phone | Emergency Phone | A= Active duty, S=Stand by, N= Not available
[6 empty] | Day 1 AM | Day 1 PM | Day 2 AM | Day 2 PM | Day 3 AM | Day 3 PM
Lead #1 | CE | CE SME #1 |  |  |  | A | S | A | S | S | S
Lead #2 | HR | HR SME #2 |  |  |  | N | A | A | S | S | A
Lead #2 | HR | HR SME #3 |  |  |  | A | S | S | A | N | S
Lead #3 | FIN | FIN SME #1 |  |  |  | N | S | A | S | N | A
Lead #3 | FIN | FIN SME #2 |  |  |  | N | A | S | N | N | S
Lead #3 | FIN | FIN SME #3 |  |  |  | N | A | S | N | N | S
Lead #3 | FIN | FIN SME #4 |  |  |  | N | A | S | N | N | A
Lead #3 | FIN | FIN SME #5 |  |  |  | A | S | A | N | N | S
Lead #3 | FIN | FIN SME #6 |  |  |  | N | S | N | A | A | S
Lead #3 | FIN | FIN SME #7 |  |  |  | A | S | N | A | S | S
Lead #3 | FIN | FIN SME #8 |  |  |  | A | N | N | S | A | A
Lead #4 | IT | IT SME #1 |  |  |  | S | N | A | S | S | S
Lead #4 | IT | IT SME #2 |  |  |  | A | N | A | S | S | S
Lead #4 | IT | IT SME #3 |  |  |  | A | N | A | S | A | S
Lead #5 | Legacy | Legacy SME #1 |  |  |  | A | S | A | N | A | A
Lead #5 | Legacy | Legacy SME #2 |  |  |  | A | S | A | N | A | S
Lead #6 | Integration #1 | Int SME #1 |  |  |  | S | N | A | N | A | A
Lead #7 | Integration #2 | Int SME #2 |  |  |  | S | N | A | N | N | N
Lead #8 | Integration #3 | Int SME #3 |  |  |  | N | N | A | N | N | N

## Ref data
Step execution status | Step defintion Status
Skipped | Blocked
Failed | In progress
In progress | Ready
Done